## Sheet1
BugID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Issue Type | Linked Issue
BUG_TC_01_01 | "Remember Me" checkbox. | Navigate the login page | Check the "Remember Me" checkbox. | Remember Me checkbox is not in the page | High | Front-End | TC_GUI_LOG_01_Successful_Login_Remember_Me
BUG_TC_02_01 | Price Slider is not available |  | Set Minimum Price and Maximum Price. | Price Slider is not available | Medium | Front-End | TC_FLT_02: Verify Filtering Products by Price Range Slider
BUG_TC_02_02 | Related Products section didn't show | Open the website, Navigate to Air Fryer XL., Open View page for "Air Fryer XL". | A "Related Products" or "You Might Also Like" section is visible, containing 3–6 relevant product cards from the same category. | "Related Products" or "You Might Also Like" section didn't show | Medium | Front-End | TC_REL_01: Verify Related Products Section Rendering
BUG_TC_02_03 | Related Products section is not showing. | Open the website, Navigate to Product., Open View page for Product. | The user should be redirected to the clicked product page | Related Products section is not showing. | Medium | Front-End | TC_REL_02: Verify Related Product Card Navigation
BUG_TC_02_04 | Blank page when Search with Non-Matching Query | Open the website, Click on the search bar, Enter a non-matching query into the search bar. | Grid displays zero products and shows a clear message: "No matching products found." | No grid shown only blank page. | Low | Front-End | TC_SCH_02: Verify Search with Non-Matching Query
BUG_TC_03_01 | No Errors or message when making duplicate category | Open "Add Category" modal as Admin.,Enter the name., add the discerption , Click "Save Category". | Creation fails with an error shows | Creation failed, ​however there's no message or error showed what's the problem | Medium | Front-End | TC_CAT_02_Admin_Create_Category_Duplicate
BUG_TC_03_02 | No edit button for the categorys | Select category Home & Kitchen and click "Edit". Update Description and change Parent Category assignment. Click "Update Category" | Changes saved successfully | There's no edit button to do this action. | High | Front-End | TC_CAT_03_Admin_Edit_Category_Success
BUG_TC_03_03 | System didn't Prevent deletion of a category with assigned items | Find category Spotrs in Admin Panel., 2. Click "Delete". | System Prevent deletion and displays warning | System didn't Prevent deletion | Critical | Front-End | TC_CAT_05_Admin_Delete_Category_With_Assigned_Items
BUG_TC_03_04 | System didn't Prevent Rename category with duplicate name | PUT /api/category/{id} | 400 Bad Request ("Category name already exists.") | 200 OK | High | API | TC_CAT_013
BUG_TC_03_05 | System didn't Prevent deletion of a category with assigned items | DELETE /api/category/{id} | 403 Forbidden, System Prevent deletion | 200 OK | Critical | API | TC_CAT_017
BUG_TC_04_01 | System didn't Prevent Exceeding quantity | Navigate to product detail page for Mountain Bicycle , Attempt to input quantity 1, Click "Add to Cart", Attempt to input quantity 9, Click "Add to Cart" | Quantity don't exceed than the number in stock or a warning shows. | the item in the cart quantity is 10 | High | Front-End | TC_CART_06_Prevent_Exceeding_Stock_Quantity_In_Cart
BUG_TC_04_02 | System didn't Prevent Exceeding quantity inside the cart | Navigate to product detail page for Mountain Bicycle , Attempt to input quantity 1, Click "Add to Cart", go to cart , Attempt to input quantity 10 | Quantity don't exceed than the number in stock or a warning shows. | Quantity exceed than the number in stock | High | Front-End | TC_CART_07_Prevent_Exceeding_Stock_Quantity_Inside_The_Cart
BUG_TC_04_03 | System didn't warn about clearing cart | Navigate to Shopping Cart page. Click "Clear Cart" button. Verify appearance of confirmation modal popup. Click "Cancel" / "Close". | Confirmation modal appears with message asking if user is sure they want to clear all items. Clicking "Cancel" dismisses modal and preserves cart items. | No confirmation modal appeared | High | Front-End | TC_CART_05_Clear_Cart_Confirmation_Modal_Prompt
BUG_TC_04_04 | System returned an item with the item requsted | POST /api/cart/items | 200 OK Returns CartDto | 200 OK, but returend item id 10 with the id 27 | High | API | TC_CART_004
BUG_TC_04_05 | System wont change the quantity of the items in the cart | PUT /api/cart/items/{cartItemId} | 200 OK (Returns updated CartDto with recalculated totals) | 400 Bad Request, "Cart item not found." | High | API | TC_CART_011
BUG_TC_04_06 | System wont change the quantity of the items in the cart | PUT /api/cart/items/{cartItemId} | 200 OK (Returns updated CartDto without deleted item) | 400 Bad Request, "Cart item not found." | High | API | TC_CART_014
BUG_TC_05_01 | System returned all items | GET /order?page=1&limit=3 | Status 200 OK, returns 3 orders per page with metadata. | Status 200 OK,returened all orders | High | API | TC_ORD_006
BUG_TC_05_02 | Orders are not sorted from highest to lowest price. | GET /api/order?sort=totalAmount_dec | Status 200 OK, orders are sorted from highest to lowest price. | Status 200 OK,orders are not sorted from highest to lowest price. | High | API | TC_ORD_008
BUG_TC_05_03 | System didnt return canceled orders | GET /api/order?sort=status=Cancelled | Status 200 OK, all returned orders have status "Cancelled". | Status 200 OK,returened all orders | High | API | TC_ORD_007
BUG_TC_05_04 | System didnt return matching results | GET /api/order?shippingAddress=jordan | Status 200 OK, returns matching results regardless of upper/lower case. | Status 200 OK,returened all orders | High | API | TC_ORD_009
BUG_TC_05_05 | System didnt filter results | GET /api/order?shippingAddress=@ | 200 OK with filtered results or an empty array [] when no match is found. | Status 200 OK,returened all orders | High | API | TC_ORD_010
BUG_TC_05_06 | System didnt Allow to patch the order shipping address | PATCH /api/order/11/Status, { "ShippingAddress" : "Jordan" } | Returns a success message when a resource is edtied | 405 Method Not Allowed | High | API | TC_ORD_020
BUG_TC_06_01 | Review submission is allowed for Unverified Purchase | Navigate to "Non-Stick Cookware Set" product page. Attempt to click "Write a Review" button Write a Review with 1 star click submit | Review submission is disabled/blocked | Review is posted successfully. | High | Front-End | TC_REV_02_Unverified_Purchase_Review_Restriction
BUG_TC_06_02 | No delete button for the reviews | User A navigates to the review section of the product. ​Locate User A's review and click the "Delete" icon. ​Confirm deletion in popup dialog. | Product average rating automatically recalculates to 1.0 star (based on remaining User B review). | There's no delete button for the reviews | High | Front-End | TC_REV_03_Owner_Delete_Own_Review_Success
BUG_TC_06_03 | No option for the admin to delete the reviews | Admin navigates to product page or Admin Moderation Panel. Locate User B's review. Click "Delete Review". Confirm deletion. | Review is deleted successfully. Product average rating updates accordingly. | There's no option for the admin to delete the reviews | High | Front-End | TC_REV_04_Admin_Delete_Any_Review
BUG_TC_07_01 | Add item to wishlist heart toggle off | Navigate to Product Catalog page. open "Laptop Pro 15"" card detail page and click heart icon on Observe heart icon visual state and confirmation message. | Heart icon toggles to active state. Product is saved to Wishlist and confirmation alert appears | Product is saved to Wishlist and confirmation alert appears but the heart state isn't active | High | Front-End | TC_WSH_01_Add_Item_To_Wishlist_Heart_Toggle
BUG_TC_07_02 | Cant remove item from wishlist by heart toggle off | Navigate to " Non-Stick Cookware Set" product page. Click the filled heart icon to untoggled it. | Heart icon reverts to inactive state. Product is removed from the user's wishlist in the database. | System showed alert that the item is saved to the Wishlist and confirmation alert appeared and the heart state isn't active | High | Front-End | TC_WSH_03_Remove_Item_Via_Heart_Toggle_Off
BUG_TC_08_01 | Sales page needed |  | System recalculates and displays sales metrics and dynamic charts strictly corresponding to transactions within September 2026. | No sales page available to check | Critical | Front-End | TC_REP_01_Filter_Revenue_Report_By_Date_Range
BUG_TC_08_02 | Range filter needed |  | Visual chart renders correctly without console errors. Hovering over data points shows accurate date and daily revenue figures. | There's no filter button to preform this action | Critical | Front-End | TC_REP_02_Render_Dynamic_Revenue_Chart
BUG_TC_08_03 | “Low stock” flags | Navigate to Admin > Products. Navigate to Mountain Bicycle . Navigate to4K Smart TV 55". | “Low stock” flags active products at 10 units remaining or fewer. | There's no flag showed up | High | Front-End | TC_REP_02_Render_Dynamic_Revenue_Chart
BUG_TC_09_01 | Page 404 Not found message | Go to /XXYZ | Website displays zero products and shows a clear message: "404 Not found." | Website Redirects you to home page not showing any message | High | Front-End | TC_GUI_ERR_01_404_Page_Not_Found
BUG_TC_09_02 | "Access Denied" error screen | Log in as customer_user Type the admin URL /admin directly into the browser address bar and press Enter. | An "Access Denied" error screen is displayed with a button to return to the Home page. | "Access Denied" error screen didn't show | High | Front-End | TC_GUI_SEC_02_Customer_Blocked_From_Admin_Portal